## Summary
S.No. | Trainee Task | Required Days
1 | Java Basic clearance. | 5 Day
2 | Database, normalization techniques & backup info | 10 Days
3 | Eclipse configuration and deployment techniques | 1 Day
4 | E- Git | 7 Day
5 | Web project creation | 6 Day
6 | Java MVC Information | 7 Day
7 | Current system analysis. | 15 Days
8 | Software SRS | 10 Days

## Basic
Task 1 | Study Below OOPS Concept With Example | 5 Day
1 | Object
2 | Class
3 | Data Abstraction & Encapsulation
4 | Inheritance
5 | Polymorphism
6 | Dynamic Binding
7 | String Manipulation
8 | Collection Framework
Task 2 | Study Database, normalization techniques & backup info With Example | 10 Days
1 | Database normalization (Norm Form 1,2,3NF) To remove duplication & to achieve data integrity.
2 | Indexing
3 | Get Force Motor Sheet & Normalize the data
4 | Create Database structure
5 | Create Database using Mysql.
6 | How to maintain back up of mysql server data with DR Conditions.
Task 3 | Study Eclipse configuration and deployment descriptor | 1 Days
1 | Eclipse Configuration(with E-git) & Apache Tomcat 7
2 | Deployment methods using Apache tomcat 7
3 | Study Apache tomcat port configuration.
4 | Catalina file info.
Task 4 | Study E - Git | 7 Days
1 | Configure/Setup E- Git online.
2 | Fork Mutha Group main repository.
3 | Push, Pull, Branch, Commit.
4 | Issue Handling
Task 5 | Study Web project creation | 6 Days
1 | Create new Web Project.
2 | With Database connectivity.
3 | With Data/File Upload
4 | Open File stored in DB
5 | Deploy In Apache Tomcat 7 with two ways(Direct deployment & Site Deployment)
Task 6 | Study Java MVC Information | 7 Days
1 | What is MVC
2 | What is use and advantage of Model,View & Controller
3 | Create MVC Structure.
4 | With Database connectivity.
5 | With Data/File Upload
6 | Open File stored in DB
7 | Deploy In Apache Tomcat 7
8 | Compare time to modify source as per requirement without MVC.
Task 7 | Study Current system analysis. | 15 Days
Source code Analysis , deployment & Backup
1 | Homepage
2 | Mutha Group MIKI(Open source System)
3 | IT Tracker
4 | ComplaintZilla
5 | ECN
6 | DVP BOSS
7 | Foundry & Machine Shop MIS System
8 | Daily Reports
9 | Auto Mail Systems
10 | ODK System(Open source System)
Task 8 | Study Software SRS | 10 Days
1 | Study What is Software SRS.
2 | How to implement.
3 | Create Force Motor Software SRS Format
Go Live..