## Work Sheet
Date | IT Software Working Task
2016-08-06 | Learn About ODK & Configuration techniques for ODK Aggregate for local install....Done | Problem Noticed
| Database version Mysql 5.1 + is required. | Apache tomcat 6.0 required, Currently using 7.0
| Checking patch not working & database incompatibility. | Mysql 5.7 required Currently using 5.0
| Have to migrate Mysql to higher version. | Data packet size not matched to import current data in Mysql
2016-08-07 | Checking higher database versionfor local ODK.
Egit source check for solution.
Exceeded Quota limit for cloud aggregate.
Working on Mysql Community server 5.7 and Tomcat 7 for local Aggregate.
2016-08-08 | Deployed on Tomcat 7 showing failed to open login page of ODK.
Only work and support available to tomcat 6
Install Tomcat 6 for local ODK.
Reconfigure using Tomcat 6 and Mysql 5.7…local install success.
2016-08-10 | DMS Documentation(SOP) created and updated to users and MIKI.
Give demo to ballal sir and approve.
New Requirement Received from Ballal sir in DMS…..In Progress.
Working on Interface between mobile and ODK Local using static IP Test..config fail.
2016-08-11 | Reconfigure ODK Aggregate using new instance.
Configure using static IP from BSNL connection(117.223.26.227)
Set up ODK Aggregate with Mysql 5.7 as localhost,3306 and ODK Instance as 117.223.26.227.
All set for local ODK Aggregate.
Add Admin users.
Import setting in ODK Collect Username and Password generated in ODK Aggregate.
2016-08-12 | Working On Local Interface between ODK Aggregate and ODK Collect.
Import ODK Local database.
Import Sample Form in ODK Aggregate Local.
Analyse database structure of ODK Aggregate Local.
2016-08-13 | Update ODK Aggregate configuration for send receive using static IP test.
Party wise work order report bug fix
Auto Mail for Pending Approval Alert……2 days required.....Done.
2016-08-14 | Vendor Boring receipt Changes received from ADG....Done.
Auto Mail for Pending Approval Alert done….
Boring segregation required in Foundry MIS received from Mr. Nade sir….4 days required....Done.
2016-08-17 | Boring Segregation
2016-08-18
2016-08-19 | IT User wise Usage report Structure New Joinee Training for Inhouse Software
2016-08-20 | Without PO GRN Auto Mailer...IT MOM.....Done.
2016-08-21
2016-08-22 | On Leave
2016-08-23 | Tuesday
2016-08-24 | New Joinee Training for Inhouse Software. In pending approval Auto Mailer update approver name¦ Department...ADG (Not in ERP)
2016-08-25 | DMS DAtabase Update , without WO issue Subcontract Auto Mail, Training Kit for IT New Users
2016-08-26
2016-08-27
2016-08-28 | ODK Setup DVPBOSS Updated SOP upload
2016-08-29
2016-08-31
2016-09-01 | IT Tracker User wise count and bug fix.
2016-09-02 | ERP MOM, DMS User wise Rights & history for read files.
2016-09-02 | Create DMS SRS, DMS User wise Rights History for read files,Bug Fix, History for newly added files. IT MOM Sheet Prepared.
2016-09-03
2016-09-04
2016-09-05
2016-09-07 | MOM with Covacsis technologies for foundry furnace unit Analysis, Installation and Updation.
2016-09-08
2016-09-09 | IT MOM, Software and Hardware analysis.
2016-09-10 | Application compilation check on remote machine
2016-09-11 | Bill wise purchase details...Vivek sir Meeting Samant
2016-09-12
2016-09-13 | MOM Updation and maintain documents.
2016-09-16 | ComplaintZilla Analysis for Internal complaints, Software Review. Update new drop down in ComplaintZilla for Complaint Type, Update in automailer and all site. Debug final check & deploy. New User Training & review.
2016-09-17
2016-09-18
2016-09-21
2016-09-22
2016-09-23 | PO Validity reminder Auto Mail,Party wise WO report issue
2016-09-24
2016-09-25
2016-09-26 | Maintain SRS Documents.
2016-09-28 | Without PO GRN Auto Mailer for Jaideep SIr above 1000...IT MOM
2016-09-29 | New Soft user training.

## Priority
SUMMARY
S.No | Name | Priority | Status | Required Days | Start Date | Upto Date | Worked Days
1 | ODK | High | Configured successfully | 40 Days | 2016-08-06 | 2016-08-13 | 7 days
2 | Create DMS SRS, DMS Customization(Ballal R.S.) History & User wise Access required,Bug Fix | Medium | Closed | 6 Days | 2016-09-02 | 2016-09-05 | 3 and 1/2 days
3 | Auto - Mail for Pending approval list(Kunal VM) | High | Closed | 3 Days | 2016-08-13 | 2016-08-14 | 2 Days
4 | Boring Segregation | High | Closed | 4 Days | 2016-08-17 | 2016-08-18 | 2 Days
5 | Database Centralisation ERP & Local : Get master |  | Pending
6 | Conference hall booking. calender....Mr. Govind Bharmgunde & Changes in design | Medium | Pending | 4 Days
7 | Without PO GRN Auto Mailer...IT MOM | Medium | Closed | 3 Days | 20/08/2016 | 21/08/2016 | 2 Days
8 | Vendor Portal....Sousri sir | Medium | In Progress | 30 Days
9 | New Joinee Training for Inhouse Software | High | Closed | 3 hrs | 2016-08-19 | 2016-08-19 | 3hrs
10 | IT User wise Usage report | Medium | Pending | 3 Days | 19/08/2016, 01/09/2016 | 2016-09-02 | 2 and 1/2 Day
11 | Vendor Portal Software SRS | High | In Progress | 5 Days
12 | Visitor Monitoring | Medium | Pending
13 | SMS API | Medium | Pending
14 | In pending approval Auto Mailer update approver name¦ Department...ADG (Not in ERP) | High | Closed | 3 Days | 2016-08-24 | 2016-08-24 | 1 Day
15 | New Joinee Training for Inhouse Software | High | Closed | 3 hrs | 2016-08-24 | 2016-08-24 | 3hrs
16 | without WO issue Subcontract Auto Mail | High | Closed | 3 Days | 2016-08-25 | 2016-08-27 | 3 Days
17 | Training Kit for IT Software Developers | High | Closed | 1 hr | 2016-08-25 | 2016-08-25 | 1 hr
18 | Asset Portal in IT Tracker | Medium | Pending
19 | IT Tracker call transfer to makarand update | Medium | Pending
20 | ODK Setup DVPBOSS Updated SOP upload | Medium | Closed | 5 Days | 2016-08-28 | 2016-08-31 | 3 Days
21 | System Health check report | Medium | Pending | 4 Days
22 | ERP MOM | Medium | Closed | 1 | 2016-09-02 | 2016-09-02 | 3hrs
23 | ERP User Wise Count | Medium | Pending
24 | ERP Auto Mailer(Reconfigure to erp@muthagroup.com) | Medium | Pending | 1 Day
25 | MOM with Covacsis technologies for foundry furnace unit Analysis, Installation and SRS. | High | Closed | 2 Days | 2016-09-07 | 2016-09-08 | 2 Days
26 | ComplaintZilla for internal complaints update...by PRM. | Medium | Closed | 8 Days | 16/09/2016 | 22/09/2016 | 5 Days
27 | Application compilation check on remote machine | Medium | Pending | 1 Day | 2016-09-10 | 2016-09-10 | 1 Day
28 | Database monitoring | Medium | Pending
29 | DVP Boss Training & requirement gathering to Samant | Medium | Closed | 1 | 2016-09-12 | 2016-09-12 | 1 Day
30 | Auto-Mail GUI For email configuration | Medium | Pending
31 | Maintain DR Document | High | Pending
32 | Bill wise purchase details & Excel Export...Vivek sir | High | Closed | 2 | 2016-09-11 | 2016-09-12 | 2 Day
33 | Tootling Project | High | Pending
34 | PO Validity reminder Auto Mail | High | Closed | 4 Days | 23/09/2016 | 25/09/2016 | 3 Days
35 | Party wise WO report issue | High | In Progress | 1 | 23/09/2016 |  | 2 Hr
36 | Inter-Company Automail.....from Kharat sir | High | Pending
37 | Without PO GRN Auto Mailer for Jaideep SIr above 1000...IT MOM | High | Pending | 1 | 28/09/2016 | 28/09/2016 | 1 Day
38 | Find blob contents type | High | Pending
39 | Backup Process Check | High | monthly
40 | ComplaintZilla updates for internal complaints and bug fix engine. | High | Pending
41 | Maintain SRS Documents | Medium | Closed | 1 | 26/09/2016 | 26/09/2016 | 1 Day

## .
Low
Medium
High
Show Stopper